## Sheet2
Stages of the project | Start date | End date | Duration in days | % Complete | Link followed to prepare this gantt chart: https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/
Stage 1: Decision of the topic | 2020-02-24 | 2020-02-26 | 3 | 100%
Stage 2: Analysis of realted works | 2020-02-27 | 2020-03-04 | 7 | 100%
Stage 3: Research questions Decision | 2020-03-05 | 2020-03-08 | 4 | 100%
Stage 4: Data mining methodology Decisions | 2020-03-09 | 2020-03-10 | 2 | 100%
Stage 5: Data Understanding | 2020-03-11 | 2020-03-14 | 4 | 100%
Stage 6: Data Preparation | 2020-03-15 | 2020-03-25 | 8 | 100%
Stage 7: First Prediction task | 2020-03-26 | 2020-05-01 | 7 | 100%
Stage 8: Second prediction task | 2020-04-02 | 2020-04-06 | 5 | 100%
Stage 9: Evaluation of results | 2020-04-07 | 2020-04-18 | 12 | 100%
Stage 10: video, Report, decision of possible future works | 2020-04-19 | 2020-04-24 | 6 | 100%